## Actual
|  | 15th Feb | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Easter | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14
Report
Create Account
Upload Template
Share with lecturer | bar: Wk7; Wk10; Wk12
Read guidelines | bar: Wk11 to Wk12
Deliverables
Create GIT repo
Share with lecturer
Commit regularly | bar: Wk14
Record the prototype | bar: Wk12
Submit VIVA | bar: Wk14
Submit Report | bar: Wk14
Research Methodology
Set hypothesis | bar: Wk12
Set research questions | bar: Wk12
Set research methods | bar: Wk12
Design research pipeline | bar: Wk11 to Wk12
Finalise section in report | bar: Wk12
Literature Review
Review datasets
Review algorithms (SOA)
Review evaluation metrics
Finalise section in report
q
Prototype
Find tutorial
Replicate tutorial | bar: Wk8 to Wk11
Create custom dataset | bar: Wk7
Tweek prototype | bar: Wk7 to Wk11
Generate evaluation results | bar: Wk10; Wk12
Discussion of results
Write prototype evaluation | bar: Wk13 to Wk14
Write dataset evaluation | bar: Wk13 to Wk14
Write hypothesis testing | bar: Wk13 to Wk14
Write project evaluation | bar: Wk13 to Wk14
Finalise section in report. | bar: Wk14
Other sections
Finalise conclusion & recommendations | bar: Wk14
Finalise introduction | bar: Wk14
Finalise abstract | bar: Wk14

## Projected
|  | 15th Feb | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Easter | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14
Report
Create Account
Upload Template
Share with lecturer
Read guidelines | bar: Wk7 to Wk12
Deliverables
Create GIT repo
Share with lecturer
Commit regularly | bar: Wk7 to Wk9
Record the prototype
Submit VIVA
Submit Report
Research Methodology
Set hypothesis
Set research questions
Set research methods
Design research pipeline
Finalise section in report
Literature Review
Review datasets | bar: Wk10 to Wk11
Review algorithms (SOA) | bar: Wk10 to Wk11
Review evaluation metrics | bar: Wk10 to Wk11
Finalise section in report | bar: Wk11
Prototype
Find tutorial
Replicate tutorial
Create custom dataset | bar: Wk7
Tweek prototype | bar: Wk7 to Wk9
Generate evaluation results | bar: Wk8 to Wk10
Discussion of results
Write prototype evaluation | bar: Wk11 to Wk13
Write dataset evaluation | bar: Wk11 to Wk13
Write hypothesis testing | bar: Wk11 to Wk13
Write project evaluation | bar: Wk11 to Wk13
Finalise section in report. | bar: Wk11 to Wk13
Other sections
Finalise conclusion & recommendations
Finalise introduction
Finalise abstract